## Sheet1
Track | Name | WBS | Git | Content(s) | Format(s) | PWS Section | PWS#
PM | Non-disclosure/Non-Use Agreement | Q1 |  |  |  | 6.1 | 1A
PM | Quality Control Plan [QCP] | Q1 | documents | an effective quality control program |  | 1.6.1 | 1B
PM | Phase-out Migration Plan | Q4 | documents | elaborates the artifacts to be transitioned on the Project Repository, and a schedule for transition completion |  | 1.6.17 | 1C
PM | Program Management Plan (PMP) | Q1 | documents | strategy to accomplish the tasks and include the risk, quality and technical management approach, work breakdown structure (WBS), schedule management approach, schedule, cost requirements, and proposed staffing |  | 5.2 | 2
PM | Program Schedule and Monthly Updates | Monthly | documents | schedule, updated monthly |  | 5.2 | 3
PM | Monthly Progress Report | Monthly |  | includes project status and financial management reporting |  | 5.2 | 4
PM | Quarterly Strategic Communications Message | Quarterly | documents | project progress and feasibility of transition to production |  | 5.2 | 5
A | Artifact Repository | Q1 |  | Project Gits |  | 8.2 | 1AA
A | Website | Q1 → Q4 | Website | website, infographics to showcase the contents of the VDM and MVDM Subset | HTML, Javascript (d3.js) | 5.3.2 | 13
A | FileMan TEST VISTA [“nodeVISTA”] | Q1 → Q4 | nodeVISTA | a test VISTA (“nodeVISTA”) that hosts different test datasets (“nodeVISTA Scenarios”) | VISTA System, Vagrant |  | E3
A | Document Generators | Q1 → Q3 | documents | Programmer documentation will be generated using tools such as Sphinx (http://sphinx-doc.org/) and JSDoc (http://usejsdoc.org/). Important Markdown-formatted documents need to be translated into PDF and HTML | Various |  | E4
B | Machine Processable VISTA Data Model (VDM) “Read Only” | Q1 | VDM | vdm.jsonld, the native VISTA data model in JSON-LD based on one or more dd.jsonld's. VDM Maker, a program that creates vdm.jsonld from dd.jsonld's. This version will support query/read (“VDM (read)”). | JSON-LD, Python, Javascript | 5.3.1 | 7.1
B | Machine Processable VISTA Data Model (VDM) | Q2 → Q4 | VDM | vdm.jsonld, enhanced by write-data in _dd.jsonld_s and rpc.jsonld. VDM Maker must process more information from dd.jsonld's and process rpc.jsonld. | JSON-LD, Python, Javascript | 5.3.1 | 7.2
B | Date-stamped FileMan Data Model Implementations (Definitions) (cross refs, triggers ...) | Q1 → Q2 | VDM | dd.jsonld, a data dictionary captured in JSON-LD DDJLD Maker, a program that caches and interprets the dictionaries from VISTAs in JSON-LD form. MUMPS code reduction will be needed for write-back support | JSON-LD, Python, Javascript | 5.3.1 | 8
B | RPC Model | Q1 → Q3 | VDM, nodeVISTA | formal definition of the model implicit in “write-back RPCs”, rpc.jsonld. Required for write support in vdm.jsonld (#7.2/#E2.2). Created with RPCJLD Maker. It may encompass VISTA Options (file 101) too | JSON-LD, Python |  | E1
B | VDM Package “Read-only” | Q1 | VDM | a package that implements the VDM inside a VISTA. It will allow any FileMan data to be queried according to the VDM. | Javascript (node.js), MUMPS (KIDS) |  | E2.1
B | VDM Package | Q1 → Q4 | VDM, nodeVISTA | Will add support for creating, updating and deleting (full CRUD) VISTA Data enabled by a write-back supporting VDM (#7.2). Initial write-back testing (in Q1) will be directly against nodeVISTA (“nodeVISTA Commands”) | Javascript (node.js), MUMPS (KIDS) |  | E2.2
B | (Document) Approach to “Live VDM” Maintenance of Current State | Q4 | VDM (Wiki) | In a wiki page, describe ways in which dd.jsonld definitions and hence vdm.jsonld could keep pace with changes in VISTAs | Markdown | 5.3.1 | 9
B | Date Stamped (Application) Meta Data for lab, surgery and other applications | Q2 | VDM | Metadata Cacher that queries meta-data using VDM package (Read) | Python, JSON-LD | 5.3.3 | 15
B | Machine-processable [PIKS] Annotations | Q2 | VDM | Distinguish patient data from other types of VISTA data in a formal definition piks.jsonld. A VDM PIKS definition enables MVDM PIKS which in turn enables patient-centric security (#28) | JSON-LD | 5.3.4 | 18
B | Software code [for PIKS] | Q2 | VDM | PIKS Annotation Generator. Relies on VDM Package (Read) to create a piks.jsonld | Python | 5.3.4 | 19
B | Prototype query access to VISTA Data against VDM [“FQS”] | Q2 | VDM | Example Query clients that query (read-only) nodeVISTA using a REST-based FileMan Query Service (FQS) implemented over VDM Package (Read) | Javascript, Python, JSON-LD | 5.4.1 | 25
B | Prototype Web-Based Query Interface to FileMan [VDM] Data | Q2 → Q3 | VDM | FQS Web Client for using VDM Package (Read) | Javascript | 5.4.1 | 33
C | Master VISTA Data Model (MVDM) “Read-only” | Q1 → Q2 | MVDM | mvdm.jsonld, a formal “MVDM Subset” definition with much of the scope of the VPR RPC which must be formally captured in vpr.jsonld. | JSON-LD | 5.3.2 | 10.1
C | Master VISTA Data Model (MVDM) | Q2 → Q4 | MVDM | full CRUD support rounded out for mvdm.jsonld. | JSON-LD | 5.3.2 | 10.2
C | [MVDM over VDM] Heuristic (mapping) code “Read-only” [_MVDM Module_] | Q2 | MVDM | mapping tables and rules implemented in a MVDM module that delivers a read-only version of MVDM over the VDM Package “Read-only”. | Javascript (node.js), JSON | 5.3.2 | 11.1
C | [MVDM over VDM] Heuristic (mapping) code [_MVDM Module_] | Q3 → Q4 | MVDM | full CRUD support added to MVDM Module (Read). | Javascript (node.js), JSON | 5.3.2 | 11.2
C | [MVDM] Normalization Reports | Q2 → Q4 | MVDM (Wiki) | Documents VDM to MVDM mapping as implemented in Deliverable #11. | Markdown | 5.3.2 | 12
C | Report on [MVDM] Exposure of older models | Q4 | MVDM (Wiki) | Describe how older, cruder models could be handled in the MVDM | Markdown | 5.3.2 | 14
C | Prototype Patient-centric Data Security | Q3 → Q4 | MVDM | First document and then provide a self- contained prototype (“Patient Security Prototype”) that shows how PIKS- enabled annotations enable patient-centric secure queries. The prototype will enhance FQS and have an example client | Javascript, Markdown | 5.4.1 | 28
C | VISTA Application model(s)/Prototype(s) [Tests] | Q2 → Q4 | MVDM | MVDM write back tests (tier 1 through 3), enabled by mvdm.js configurations. Test scenarios for Deliverable #11. | Javascript, Python | 5.4.2 | 35
C | Meta-model(s) [VPR] Prototype(s) | Q2 → Q3 | MVDM | Test code that shows how well the MVDM supports VPR (Read-only) convenience methods - read-only side of #35 | Javascript, Python | 5.4.2 | 36
D | Prototype Web-based Rules Hub | Q3 | MVDMmap | Prototype a sharable, crowd source-able mechanism to exchange and grow a library of open, standards-based, validated, and exchangeable transformation rules | Web-based interface | 5.4.1 | 32
D | Reference model(s)/Prototype(s) [“FHIR Translator”] | Q3 → Q4 | MVDMmap | Prototypes that demonstrate mapping from MVDM to FHIR | Javascript and/or other translation rules languages | 5.4.2 | 39
D | Document VISTA-ese vs. FHIR | Q3 → Q4 | MVDMmap | Human-readable mapping descriptions | Markdown | 5.4.2 | 40